MainLine Project Management Software Revision 2.5

Copyright 1992-1998 by Minuteman Systems

----------------------------------------

Registration Information

This  program  is  supplied as Shareware.  This means that you may

evaluate  the  program  for  free,  but  are  required  to  pay  a

registration  fee if you keep it and use it.  To register fill out

the  order  form  at  the  end of this document and send it with a

check or money order for $29.95 to

Minuteman Systems, PO Box 152, Belmont, Massachusetts, 02178.

telephone: (617)489-5639           internet: bck@world.std.com

Registration payment can also be made via a credit card on the

Internet. Go to site www.shareit.com and register program # 100853.

As a registered user, you will receive

o  A copy of the Advanced Edition of MainLine with

- Ability to handle more tasks (150)

- Additional features - Project Import, Task Copy, Searching

o  A printed and bound copy of the detailled 50-page User's Manual.

o  Free updates for one year.

o  Telephone service.

------------------------------------------------------------------

Table of Contents

1. Features ............................................... Page-1

2. Using The Program  ..................................... Page-2

2.1  Installation and Startup  ......................... Page-2

2.2  Moving Around The Screen  ......................... Page-2

2.3  Calling Up Commands ............................... Page-3

2.4  Shortcut - Frequently Used Commands ............... Page-3

2.5  Basics of Editing and Generating Reports  ......... Page-3

2.6  Types Of Tasks and Milestones ..................... Page-4

2.7  Notes on Dates and Calculations ................... Page-4

3. Command Listing  ....................................... Page-6

3.1  Filing  ........................................... Page-6

3.2  Edit  ............................................. Page-6

3.3  Search  ........................................... Page-7

3.4  Display ........................................... Page-7

3.5  Print ............................................. Page-7

3.6  Options ........................................... Page-8

4. Service  ............................................... Page-9

5. Order Form ............................................ Page-10

1.  Features

MainLine  is  a Project Management Tool.  It's primary function is

to develop a chart to show the relationships of tasks in a project

and  their  durations  in  time.   The  format of the schedule has

several  unique  characteristics  which  go  well  beyond  what is

typically  offered  as  "Gantt"  or "Pert" charts in other project

management programs;

- Several tasks may be shown on one line on the schedule.

Conventional Gantt charts have only one task per line.

With MainLine, schedules can be drawn in a far more compact

and readable format. You can often get "a whole schedule on

a single page"

- All MainLine reports, including the Schedule, can be output

as text files. This means that the schedule can be widely

distributed to other people and they can read it with almost

any word processor or they can print it on almost any printer.

They do not need to have a copy of MainLine themselves. Many other

project management tools require that the recipient have a copy

of the program if they are to view the schedule.

MainLine  is written to facilitate initial entry of a schedule, as

well  as performing updates.  Also, its important to insure that a

schedule remain "manageable" if it has a lot of entries, or if its

necessary  to  make  a  lot  of  changes as time goes n.  MainLine

addresses  this  by  providing  a  number  of features to simplify

handling large or changing projects;

- Renumbering of tasks

- Ability to copy blocks of tasks

- Search functions to find tasks that are off-screen

- Ability to "trace" the critical path across the project

from screen to screen.

In  summary,  MainLine  was written for people who need to quickly

and easily develop project schedules and convey the information to

other people.

Page-1

2.  Using The Program

2.1 Installation and Startup

Decompress  the  program  files and install in a directory such as

C:\MAINLINE.   If  the  program was obtained as a .ZIP file from a

BBS,  it  can  be copied into the directory and decompreseed using

PKUNZIP.   If obtained from a Shareware supplier, use the supplied

INSTALL.BAT file or other installation tool.

The  executable  file  is  ML.EXE.  To run the program, at the DOS

prompt type ML followed by ENTER.

2.2 Moving Around The Screen

After  a  few  seconds  a  screen  will  be  displayed for a blank

project.

The calendar is displayed across the top of the screen.

The  duration  of  all  tasks  is identified with either "="'s (on

critical   path)  or  with  "-"'s  (not  on  critical  path.)  All

milestones have a duration of 0 and are indicated with a "*".  All

tasks  and  milestones  have  unique  identifying TASK ID numbers.

These are displayed on the schedule below the row of symbols (-,=,

or *) indicating the duration of the task/milestone.

The  up  and  down arrow keys may be used to scroll the display up

and down one task-line at a time.

When  examining  the schedule, the following other controls may be

used;

Key                Function

-------------      --------------------------------------------

Down Arrow         Advance Screen One Line

Up Arrow           Back Screen One Line

Right Arrow        Move Forwards in time.

Left Arrow         Move Backwards in Time

PAGE DOWN          Advance to Next Screen

PAGE UP            Go Back 1 Screen

HOME               Move to Top-most Screen and Start of Calendar

CTRL-T             Move to Top-most Screen

CTRL-B             Move To Bottom-most Screen

CTRL-L             Move Horizontally Left To Start of Calendar

CTRL-R             Move Horizontally Right to Latest Used Date

CTRL-F             Find Task/Milestone

+                  Follow the critical path forwards in time

-                  Follow the critical path backwards in time

"|"                Go To A Specific Line Number

"\", "/", or ESC   Activate Pull-Down Menu

Page-2

2.3 Calling Up Commands

Pressing "\" , "/", or ESC calls up a pull-down menu at the top of

the screen.  The majority of commands are activated from this.

One  entry  on the command line is highlighted.  The highlight may

be  moved  around  by  using the horizontal arrow keys (<- or ->).

Pressing  Down-Arrow  causes  a menu of choices to appear.  One of

them  is highlighted.  The Up- and Down-Arrows move the highlight.

The Right- and Left-Arrows select adjacent menus.

Pressing ENTER activates the highlighted command.  Pressing Escape

backs out of the menu system.

2.4 Shortcut - Frequently Used Commands

The  most  frequently  used  functions  of  Editing,  Adding,  and

Deleting  tasks  may  also  be used without going through the menu

system.   Type  "e",  "a", or "d" to select which function.  Enter

the task number followed by return, and the function will start.

2.5 Basics of Editing and Generating Reports

Existing  Tasks  and  Milestones are edited by activating the menu

and  selecting  "Edit"  followed  by  "Change".  A data sheet will

appear  listing  all  current  data  on  the  task  or  milestone.

Individual  entries  are  selected  by pressing the code-letter in

front  of  the data field on the sheet - i.e.  "d" for "duration",

"c"  for "description, etc.  Additional data views may be obtained

by  entering  "v".   When  done, enter "x" to exit the data-editor

with changes, or "q" to quit without implementing the changes.

New  Tasks  and Milestones may be added by using the menu- command

to select "Edit" followed by "Add Task".  You will be prompted for

basic  information  about  the  task/milestone,  and then the data

sheet will appear.

Similarly, tasks may be deleted using "Edit" followed by "Delete".

Deletions  which make it impossible to calculate the critical path

are not accepted.

Page-3

2.6 Types Of Tasks and Milestones

The  "Type" field is used to specify if the entry is a Task ("t"),

Milestone ("m"), Start ("s"), Finish ("f"), or Rollup ("r").

Tasks - Have an assignable duration and don't start until all

predecessors are met and/or a specified "wait" period has

occured. If no predecessors are specified, the task starts

on the "Start Date" that is typed in.

Milestones - Have zero duration. They have have the same start

criteria as tasks.

Start - A special type of milestone. It indicates the starting

point from which all predecessors and dates are determined

for the whole project. There must be one and one only

"Start" per project.

Finish - A special type of milestone. Used to mark the end of the

critical path for the project. There must be one and one only

"Finish" per project.

Rollup - Provides a "summary" of tasks. A Rollup task calculates

it's start and end dates based on the set of all its

predecessors. The start date of the Rollup is the earliest

of the start dates of all its predecessors. The End date of

the Rollup is the end date of the last to finish of all its

predecessors. This provides a one-task condensation of the

activity of a group of tasks.

A  sample  project is included with the program to demonstrate the

different  types  of tasks.  Use FILE and OPEN to load the project

SAMPLE.  A printout of SAMPLE is given on the next page.

2.7 Notes on Dates and Calculations

o  Each project must contain one milestone designated as the

"Start" of the Critical Path, and another designated as

the "Finish". These selections are made with the data-

sheet editor by entering "s" and "f" respectively in the

"Type" field for those milestones.

o  There must be a logical path of tasks and milestones

between the Start and Finish milestones. There may be

tasks and milestones which are partially or completely

disconnected ("hanging or ending in space"), but there

must be a set of tasks and milestones connecting the Start

and Finish together.

o  Only work-weekdays are used. Weekend-days, if entered,

are rejected.

Page-4

Project: SAMPLE                             Use:  6%  INS  MainLine Rev 2.3a

Sample Product .--------------------+---------------------+-------------------+.

Development    |__Dec '94____|_ Jan '95 ____|_ Feb '95 ___||

Schedule       |    0    1    2    3|   0    1    2    2  | 0    1    1    2  ||

|    9    6    3    0|   6    3    0    7  | 3    0    7    4  ||

Date:04-Dec-94 |MTWTFMTWTFMTWTFMTWTF|TWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMT||

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Kickoff     1 |Start    .Funding Approved   .    .    .    .    .    .    .   |

|              |*   .    .*   .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    . 14 .    .    .    .    .    .    .    .    .    .   |

|            2 | Proposal.    .    .    .    .    .    .    .    .    .    .   |

|              | =========^   .    .    .    .    .    .    .    .    .    .   |

|              |  12.    .    .    .    .    .    .    .    .    .    .    .   |

|            3 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|Develop     4 |    .    . Design Phase .    .    .    .    .    .    .    .   |

|              |    .    . ----------------------------------^   .    .    .   |

|              |    .    .  29.    .    .    .    .    .    .    .    .    .   |

|            5 |    .    . Specifications Hardware Design   .    .    .    .   |

|              |    .    . ==============^===================^   .    .    .   |

|              |    .    .  20.    .    .  22.    .    .    .    .    .    .   |

|            6 |    .    .    .    .    . Write Software    .Signoff  .    .   |

|              |    .    .    .    .    . --------------^   .*   .    .    .   |

|              |    .    .    .    .    .  24.    .    .    . 26 .    .    .   |

|            7 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|Build       8 |    .    .    .    .    .    .    .    .    . Manufacture  .   |

|              |    .    .    .    .    .    .    .    .    . =========^   .   |

|              |    .    .    .    .    .    .    .    .    .  30.    .    .   |

|            9 |    .    .    .    .    .    .    .    .    .    .    .Ship.   |

|              |    .    .    .    .    .    .    .    .    .    .    .*   .   |

|              |    .    .    .    .    .    .    .    .    .    .    . 40 .   |

|           10 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTF|TWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMT||

|    0    1    2    3|   0    1    2    2  | 0    1    1    2  ||

|    9    6    3    0|   6    3    0    7  | 3    0    7    4  ||

|     Dec '94        |    Jan '95          |    Feb '95        ||

`--------------------+---------------------+-------------------+'

Page-5

3.  Command Listing

This  section describes briefly all functions that may be accessed

by the menu-command line.

3.1 Filing

The following functions may be accessed by this command;

1. New - Restarts with the "blank" project being displayed.

2. Open - recall an existing project file. You will be

prompted for a project name.

3. Save - Save away the project file which is being worked

on. A default is always given. If you're working on a file

which was read-in, the old name is the default. You may

store it under a new name if you wish.

4. Import - Merge another project file with the project

presently being worked on.

[Function available only in Advanced Edition.]

5. Exit - Leave Program

3.2 Edit

This is the environment for changing tasks and milestones.

1. Change - Select an existing Task or Milestone to change

its data.

2. Add Task - Add one or more new tasks (Note - The Standadrd

Edition handles up to 50 tasks/milestones. The Advanced

Edition handles up to 150.)

3. Delete - Delete an existing task or milestone.

4. Find Task - Locate an existing task by its ID number.

5. Renumber - Change the Task Numbers for One, Some, or All

Tasks.

[Some/All Functions available only in Advanced Edition.]

6. Copy - Duplicate a group of tasks and milestones.

[Function available only in Advanced Edition.]

Page-6

3.3 Search

Search for tasks by

1. Description

2. 1st Header

3. Second Header

[Functions available only in Advanced Edition.]

3.4 Display

2. Add Lines - Add Blank Lines into the display.

3. Delete Lines - remove unused lines from the display.

4. Move Lines - Move a block of used lines up or down.

5. Labels - Enter or change 4 label-lines on display.

3.5 Print

1. Partial Schedule - Print a schedule report covering only

the time-span presently shown on the screen. Output file =

projectname.txt

2. All Schedule - Print a schedule report for the period

currently shown on the display through the end of the

project. Adjacent pages of the report will need to be

taped together to obtain a full horizontal view. Output

file = projectname.txt

3. Date Report - Print a report of the start and end dates

for all tasks and milestones. Output file = projectname.dat

4. Task Detail Report - List complete information on all

tasks and milestones in the project. Output file =

projectname.rpt.

Page-7

3.6 Options

Set system options.

1. Configuration - Save or Get

2. Screen - Set Column Width (80 Columns, 105 Columns

Monochrome, or 105 Columns Color), Time Scale (Days or

Weeks),  Screen ID (Show or hide, to compact data on the

screen), Set Calendar Start Date

3. Screen Foreground Color

4. Screen Background Color

5. Print Output Optins - Print To (Text File or Printer on LPT1:),

Print Width (80 or 132 Columns), Pagelength (Normal or Shortened),

Print ID (Similar to Screen ID, but for printed output.)

Page-8

4.  Service

Registered users are provided service for this program.

Telephone service is provided at (617)489-5639

Service  is  also  provided  on  the  INTERNET at

address bck@world.std.com

Page-9

Order Form

----------

Fill in the information below, and mail with a check or money order

for $29.95 to

Minuteman Systems

P.O. Box 152

Belmont, MA. 02178

Service Telephone (617)489-5639

You will receive the Advanced Edition of MainLine with additional

features, a printed and bound detailed instruction manual,

telephone support, and free updates for one year.

Name ________________________________________________________

Address _______________________________  Apt\MailStop _______

City/Town _______________________  State ___  ZipCode _______

Telephone -  Business:________________  Home:________________

Media :  ___ 5.25" floppy   ___  3.5" micro-floppy

How did you obtain this program?

--------------------------------

Service/BBS : Compuserve ___  AOL ___  Prodigy ___  Other ___

Sample: ___  Shareware Vendor :  Name _______________________

Other : _____________________________________________________

Comments

------------------

Please describe here what you like about MainLine, what you would

like to see improved, additional features you would like to see,

or make any other comments;

Page-10